## Hoja1
Javier Falcón
Development Tasks Completed | Plan Hours | Actual Hours | Planned Value | Earned Value
Registrar Turno en el sistema | 6 | 9
Sync. Dashboard y Detalles de la sucursal | 4 | 8
Post-mortem | 3 | 3
Total | 13 | 20 | 0 | 0%
Jesse Peña
Development Tasks Completed | Plan Hours | Actual Hours | Planned Value | Earned Value
Registrar Turno en el sistema | 6 | 9
Sync. Dashboard y Detalles de la sucursal | 4 | 8
Post-mortem | 2 | 2
Total | 13 | 20 | 0 | 0%
Alexander Schobel
Development Tasks Completed | Plan Hours | Actual Hours | Planned Value | Earned Value
Login del cliente (Autentificacion) | 4 | 1.2
User Register | 4 | 2.15
Forgot Password | 2 | 0.45
Post-mortem | 2 | 2
Total | 13 | 5.8 | 0 | 0%
Robert Gomez
Development Tasks Completed | Plan Hours | Actual Hours | Planned Value | Earned Value
Pedir turno (membresia, cual tiene el usuario) |  | 2.07
Adding a photo to a company |  | 10.46
Post-mortem | 2 | 2
Total |  | 14.53 | 0 | 0%
Juan Luis Mejía
Development Tasks Completed | Plan Hours | Actual Hours | Planned Value | Earned Value
Perfil de usuario (Modificar/Agregar Campos/Estetica) | 4 | 3
Modificar Vista About |  | 2
Post-mortem | 2 | 2
Total |  | 7 | 0 | 0%