## Sheet2
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 86 | 79
Project hours this cycle to date |  |  | 253 | 230
Earned value for this week |  |  | 36.4 | 30.5
Earned value this cycle to date |  |  | 100 | 93.6
Total hours for the tasks completed this phase to date |  |  | 77
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 23 | 24 | 9.0907 | 7.918
Development Manager | 5 | 3 | 3.1687 | 1.996
Planning Manager | 22 | 20 | 9.0907 | 7.918
Quality/Process manager | 22 | 20 | 9.0907 | 7.918
Support Manager | 14 | 12 | 5.9227 | 4.75
0
Totals | 86 | 79 | 36.3636 | 30.5
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Móvil- Filtrar por tipo de servicio | 25 | 25 | 9.9 | 2
Móvil- Integración todas las vistas | 40 | 40 | 15.8 | 3
Documentación | 10 | 10 | 4 | 3
Post Mortem | 11 | 0 | 0 | 3
Ajustar tiempo de espera por tipo de turno | 2 | 2 |  | 3
Ajustar asignacion de numero de ticket | 2 | 2 |  | 3