## Hoja1
Jesse Peña
Development Tasks Completed | Planned Hours | Actual Hours | Planned Value | Earned Value
Detail view design | 5 | 6
Diseño de vista
Fetch data for company details | 7 | 5
Usar data de la base de datos en la vista de android
| 12 | 11
Javier Falcon
Development Tasks Completed | Plan Hours | Actual Hours | Planned Value | Earned Value
Create mobile data models | 4 | 4
Fetch data for company details | 6 | 7
Total | 10 | 11 | 0 | 0%
Robert Gomez
Development Tasks Completed | Plan Hours | Actual Hours | Planned Value | Earned Value
El Administrador edita una sucursal |  | 0:29
Un Administrador registra una sucursal (Escenario 1: La sucursal no existe) |  | 17:05
Companies list |  | 0:55
Un Administrador registra su empresa (Escenario 2: La empresa ya existe) |  | 13:92
Un Administrador registra su empresa (Escenario 1: La empresa no existe) |  | 24:71
Total |  | 56.37
Alexander Schobel
Development Tasks Completed | Plan Hours | Actual Hours | Planned Value | Earned Value
Detail view design | 5 | 4
diseño de vistas
views coding | 6 | 3
funcionalidades de la vista
Total | 11 | 7
Juan Luis Mejía
Development Tasks Completed | Plan Hours | Actual Hours | Planned Value | Earned Value
Detail View Design | 4 | 4
Fetch Data for User Profile | 6 | 1
Re-planning | 4 | 3
Total | 14 | 8 | #REF! | #REF!