## Sheet2
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 83 | 72
Project hours this cycle to date |  |  | 83 | 72
Earned value for this week |  |  | 32.8 | 25.8
Earned value this cycle to date |  |  | 32.8 | 25.8
Total hours for the tasks completed this phase to date
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 22 | 17 | 6.56
Development Manager | 4 | 17.08 | 2.7
Planning Manager | 14 | 15 | 5.6
Quality/Process manager | 22 | 16 | 6.56
Support Manager | 21 | 6.9 | 4.4
0
Totals | 83 | 71.98 | 25.82 | 0
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Generar Plan de Ciclo 3 | 8 | 8 | 3.2 | 1
Móvil- Registrar usuario | 5 | 5 | 2 | 1
Móvil- Modificar Vista About | 5 | 5 | 2 | 1
Móvil- Modificar Vista Profile View | 5 | 5 | 2 | 1
Móvil- Modificar Vista Log in | 5 | 1.9 | 0.76 | 1
Móvil- Modificar Vista Registro Usuario | 5 | 5 | 2 | 1
Móvil- Cancelar Turno | 17 | 18 | 6.7 | 1
Móvil- Log out | 11 | 0 | 0 | 1
Móvil- Forgot password | 5 | 1.05 | 0.44 | 1
Móvil-Mostrar número de ticket al pedir turno | 16 | 14 | 6.3 | 1
Web - validación membresía de no tener eliminar opción en sucursales | 1 | 1 | 0.4 | 1
Web- Mejora Pedir Turnos |  | 7.32
web- Recibir Ticket en tiempo real |  | 5.21
Solucion a errores parte Web |  | 2.12
Arreglo servicio consumido en Web |  | 2.09
Arreglo modelos en la Web |  | 0.34