## Sheet2
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 93 | 93
Project hours this cycle to date |  |  | 176 | 176
Earned value for this week |  |  | 36.8 | 36.8
Earned value this cycle to date |  |  | 32.8 | 25.8
Total hours for the tasks completed this phase to date
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 29 | 29
Development Manager | 9 | 9
Planning Manager | 16 | 16
Quality/Process manager | 26 | 26
Support Manager | 13 | 13
0
Totals | 93 | 93 | 0 | 0
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Móvil- Modificar Vista Log in | 5 | 3.1 | 1.2 | 1
Móvil- Log out | 11 | 11 | 4.3 | 1
Móvil- Forgot password | 5 | 3.9 | 1.6 | 1
Móvil- Filtrar por tipo de servicio | 25 | 25 | 9.9 | 2
Web/Móvil- Validación tiempo de espera al tomar ticket, cierre | 16 | 16 | 6.3 | 2
Móvil- Filtrado Dashboard según el usuario | 10 | 10 | 4 | 2
Móvil- Barra de búsqueda | 32 | 32 | 12.6 | 2
Móvil- Swipe Refresh en Dashboard | 10 | 10 | 4 | 2