## Sheet2
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 98 | 83
Project hours this cycle to date |  |  | 215 | 199
Earned value for this week |  |  | 39.9 | 21.1
Earned value this cycle to date |  |  | 100 | 81.2 |  | TL | DM | PM | QPM | SM
Total hours for the tasks completed this phase to date |  |  |  |  | Registrar turno en el sistema | 9 |  |  | 9
[5 empty] | Registrar reserva de hora en el sistema | 0 |  |  | 0
[5 empty] | Backend Login |  |  |  |  | 4
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value | Link Dashboard y y Pedir Turno | 8 |  |  | 8
Team Leader | 21 | 20 | 10.78 | 5.83 | Registrar turno presencial WEB |  | 13
Development Manager | 20 | 30 | 8.1 | 8.1 | Perfil de moderador WEB |  | 15
Planning Manager | 16 | 10 | 4 | 0.9 | Desplegar información del usuario |  |  | 5
Quality/Process manager | 20 | 19 | 10.3 | 5.5 | Generar eMail de recuperar contraseña |  |  |  |  | 1
Support Manager | 17 | 7 | 7.51 | 0.9 | Eliminar Turno
0 |  |  |  |  | Post Mortem | 3 | 2 | 2 | 2 | 2
Totals | 94 | 86 | 40.69 | 21.23 | Editar perfil de usuario |  |  | 0
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Registrar turno en el sistema | 12 | 18 | 5.4 | 3
Backend Login | 7 | 4 | 3.1 | 3
Link Dashboard y y Pedir Turno | 8 | 16 | 3.6 | 3
Registrar turno presencial WEB | 10 | 13 | 3.6 | 3
Perfil de moderador WEB | 10 | 15 | 3.6 | 3
Desplegar información del usuario | 7 | 5 | 3.1 | 3 |  | 20 | 30 | 7 | 19 | 7
Generar eMail de recuperar contraseña | 8 | 0 | 0 | 3
Eliminar Turno | 10 | 0 | 0 | 3
Post Mortem | 11 | 11 | 4.9 | 3