## Sheet2
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 77 | 53
Project hours this cycle to date |  |  | 250.5 | 198
Earned value for this week |  |  | 32.4 | 15.6
Earned value this cycle to date |  |  | 100 | 83.4
Total hours for the tasks completed this phase to date
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 15 | 14 | 6.32 | 6.32
Development Manager | 17 | 15 | 7 | 7
Planning Manager | 15 | 8 | 6.32 | 4.32
Quality/Process manager | 15 | 8 | 6.32 | 4.32
Support Manager | 15 | 8 | 6.32 | 4.32
0
Totals | 77 | 53 | 32.28 | 26.28
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Integration Plan | 4 | 5 | 1.6 | 3
Code | 27 | 25 | 0 | 4
Code Review | 15 | 0 | 0 | 4
Post-mortem | 15 | 15 | 6 | 4
Documentation | 20 | 8 | 8 | 4