## Sheet2
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 39.5 | 43
Project hours this cycle to date |  |  | 39.5 | 43
Earned value for this week |  |  | 24.8 | 24.8
Earned value this cycle to date |  |  | 24.8 | 24.8
Total hours for the tasks completed this phase to date
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 4 | 6 | 2.13 | 2.13
Development Manager | 14 | 12 | 8.63 | 8.6
Planning Manager | 5 | 6 | 3 | 3
Quality/Process manager | 10 | 12 | 7.74 | 7.7
Support Manager | 5.5 | 7 | 3.3 | 3.3
0
Totals | 38.5 | 43 | 24.8 | 24.73
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Task/Planning | 7 | 9 | 4.5 | 1
Pantalla Dashboard | 14 | 14 | 9 | 1
Log in móvil | 7.5 | 6 | 4.8 | 1
Registrar Empresa | 10 | 14 | 6.5 | 1