## Sheet2
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 83
Project hours this cycle to date |  |  | 83 | 0
Earned value for this week |  |  | 16.9492 | 0
Earned value this cycle to date |  |  | 16.9492 | 0
Total hours for the tasks completed this phase to date
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 20 | 16 | 12.054 | 0.84
Development Manager | 19 | 13.5 | 10.38 | 0.705
Planning Manager | 24 | 15 | 11.5 | 1.4
Quality/Process manager | 20 | 13 | 9.98 | 0.8
Support Manager | 19 | 11 | 9.61 | 0.7
0
Totals | 102 | 68.5 | 53.524 | 4.445
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Task/Planning | 25 | 29
Elicitación de Requerimientos | 5 | 4
Aprendizaje de Tecnologías | 56 | 30
Enseñanzas de tecnología | 14 | 5
SRS | 13 | 3
Code | 27 | 3.5