## Sheet2
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 42 | 45.5
Project hours this cycle to date |  |  | 120 | 108
Earned value for this week |  |  | 33.4 | 33.4
Earned value this cycle to date |  |  | 45 | 45
Total hours for the tasks completed this phase to date
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 11.5 | 10.5 | 8.28 | 8.28
Development Manager | 11.5 | 10.5 | 6.25 | 6.25
Planning Manager | 6.5 | 7.5 | 6.3 | 6.3
Quality/Process manager | 6.5 | 8.5 | 6.3 | 6.3
Support Manager | 6.5 | 8.5 | 6.3 | 6.3
0
Totals | 42.5 | 45.5 | 33.43 | 33.43
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Aprendizaje de tecnologías | 26 | 16 | 21.0923 | 2
Enseñanza de Tecnologías | 9 | 6 | 5.3 | 2
Inspección de Requerimientos | 5 | 10 | 1.9 | 2
SRS | 10 | 13.5 | 4.9 | 1