## Sheet2
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 53.5 | 35
Project hours this cycle to date |  |  | 173.5 | 143
Earned value for this week |  |  | 21.4 | 19.8
Earned value this cycle to date |  |  | 69.4 | 67.8
Total hours for the tasks completed this phase to date
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 9.5 | 5.5 | 3.8 | 3.8
Development Manager | 12 | 10 | 4.8 | 4.8
Planning Manager | 9 | 8.5 | 2.8 | 2.8
Quality/Process manager | 12 | 5.5 | 4.8 | 4
Support Manager | 11 | 5.5 | 4.8 | 4
0
Totals | 53.5 | 35 | 21 | 19.4
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
SDS | 11 | 6 | 4.4 | 3
Mock-ups | 13.5 | 13 | 5.4 | 3
Integration plan | 4 | 0 | 0 | 3
Detailed design | 15 | 11 | 4 | 3
Mock-ups inspection | 10 | 5 | 6 | 3